## Project schedule
| Phần Mềm Quản Lý Bán Hàng | [5 empty] | Project start: | [7 empty] | 2024-12-11
Project lead
| Thành viên | Trần Hữu Duy Phương(Leader)
Nguyễn Minh Tuấn
Nguyễn Đức Mạnh
Phan Nhật Anh
[7 empty] | 2024-12-02 | [6 empty] | 2024-12-09 | [6 empty] | 2024-12-16 | [6 empty] | 2024-12-23 | [6 empty] | 2024-12-30 | [6 empty] | 2025-01-06 | [6 empty] | 2025-01-13 | [6 empty] | 2025-01-20
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2024-12-02 to 2025-01-26
 | time axis 2024-12-02 to 2025-01-26
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Khởi tạo
| Xác định và phân tích yêu cầu | Trần Hữu Duy Phương | 75% | 2024-12-11 | 2024-12-14 | 4
| Các case study trong dự án | Nguyễn Minh Tuấn | 50% | 2024-12-14 | 2024-12-16 | 3
| Tạo SRS | Nguyễn Đức Mạnh | 50% | 2024-12-16 | 2024-12-20 | 5
| Planning | Phan Nhật Anh | 50% | 2024-12-20 | 2024-12-20 | 1
Thiết kế giao diện (chi tiết hơn khi có tài liệu SRS --> chi tiết về các task)
| Tạo schedule | Trần Hữu Duy Phương | 75% | 2024-12-21 | 2024-12-25 | 5
| Xác định các vấn đề/chức năng trong TK | Nguyễn Minh Tuấn | 50% | 2024-12-23 | 2024-12-28 | 6
| Wireframe và prototype | Nguyễn Đức Mạnh | 50% | 2024-12-28 | 2024-12-31 | 4
| Hoàn thiện thiết kế | Phan Nhật Anh | 50% | 2024-12-28 | 2024-12-30 | 3
| Kiểm tra thiết kế |  |  | 2024-12-28 | 2024-12-31 | 4
Thiết kế chương trình (gồm thiết kế kiến trúc và thiết kế chi tiết chức năng)
| Tạo schedule | Trần Hữu Duy Phương | 75% | 2025-01-01 | 2025-01-05 | 5
| Xác định kiến trúc chương trình | Nguyễn Minh Tuấn | 50% | 2025-01-06 | 2025-01-10 | 5
| Luồng dữ liệu | Nguyễn Đức Mạnh | 50% | 2025-01-11 | 2025-01-18 | 8
| Thiết kế kiến trúc | Phan Nhật Anh | 50% | 2025-01-19 | 2025-01-26 | 8
| Kiểm tra thiết kế |  |  | 2025-01-27 | 2025-02-03 | 8
Thực thi (chi tiết hơn về các task, chức năng cần làm)
| Test plan (UI, chức năng) | Trần Hữu Duy Phương + Nguyễn Minh Tuấn | 60% | 2025-02-04 | 2025-02-09 | 6
| Coding | Trần Hữu Duy Phương | 80% | 2025-02-10 | 2025-02-15 | 6
| Testing và đánh giá | Nguyễn Minh Tuấn | 50% | 2025-02-16 | 2025-02-23 | 8
| Tạo tài liệu về test | Nguyễn Đức Mạnh | 50% | 2025-02-24 | 2025-02-26 | 3
| Quản lý source code | Phan Nhật Anh | 50% | 2025-02-27 | 2025-03-01 | 3
Đánh giá
| Hoàn thiện chương trinh | Trần Hữu Duy Phương | 50% | 2025-03-01 | 2025-03-07 | 7
| Báo cáo | Nguyễn Minh Tuấn | 50% | 2025-03-01 | 2025-03-07 | 7
| Đánh giá về khả năng mở rộng | Nguyễn Đức Mạnh + Phan Nhật Anh | 50% | 2025-03-01 | 2025-03-07 | 7
Insert new rows ABOVE this one

## About
SIMPLE GANTT CHART by Vertex42.com
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.